## Burndown Chart Template
Burndown Chart Template
Velocity = Total Story Points Delivered over a Sprint
The example below illustrates a basic example of a 4 Sprint Project. Being the Sprints in this case 2 weeks long this is a 2 month project.
It has 15 user stories in total. I've used the name "User Story #" in the essence of time, but you would of course write the actual user story using the format described in the other tab
Assumption: The team discards the user stories which aren't delivered
Sprint 1 |  | Story Points
admin can add drinks |  | 4 |  | 4
admin can add users |  | 3 |  | 3
customer view orderdetails front end |  | 3 |  | 2 |  |  | Note: diagrams and completed in sprint 1 so we copleted them in sprint 2
Diagrams |  | 6 |  | 3
customer view menu |  | 7 |  | 4
customer add to basket front end |  | 4 |  | 4
| Total | 27 | Velocity Sprint 1 |  | 16
Sprint 2 | [6 empty] | Note: there wasnt enough time to complete the orders page and the and customer review
Diagrams |  | 6 |  | 6
customer order details backend |  | 3 |  | 3
customer view menu |  | 7 |  | 7
admin order page |  | 4 |  | 0
customer add to basket backend |  | 4 |  | 4
Customer review |  | 3 |  | 0
| Total | 27 | Velocity Sprint 2 |  | 20
Total Story Points |  | 54 | Average Velocity |  | 18 | Which means that on average the team is delivering 9 story points per Sprint. This is known as the project's Velocity
This is an indication of execution that allows for future planning and workload management.
Traditional
Burndown Chart
Sprint | Remaining Story Points
1 | 54
2 | 18
Another option
Burndown Chart
Sprint | Remaining Story Points | Story Points Delivered
1 | 54 | 16
2 | 38 | 20
Another option
Burndown Chart
Sprint | Remaining Story Points | Story Points Delivered
1 | 54 | 16
2 | 38 | 20